## Slide 1: XYZ Company Project Status Report Presented by Shawnette Johnson

## Slide 2: Agenda
Project Accomplishments
Design Phase & Resources
Expected Completion
Remaining Forecast
Critical Path
Mitigation and Action Plans
Budget Update
Notes: Project Accomplishments
Design Phase & Resources
Expected Completion
Remaining Forecast
Critical Path
Mitigation and Action Plans
Budget Update

## Slide 3
Current Project State
XYZ Website Project
12/01/2020
Overall Status:
Remaining planned budget throughout project completion
AC $ 14, 866.00 PV $ 15, 595.00 EV $15,595.00 SPI 1 EAC $100,502.00 VAC $4,928.00
Expected Schedule Forecast | Target date | Expected completion | Status
Analysis Phase | 07/20/20 | 08/14/20 | Complete
Design Phase | 08/17/20 | 09/21/20 | In progress
Build Phase | 09/21/20 | 11/24/20 | Scheduled
Test Phase | 11/24/20 | 12/22/20 | Scheduled
Delivery | 12/24/20 | 01/07/21 | Scheduled
Key accomplishments through the end of the analysis phase
Completed all tasks for planning, layout and prototyping, content integration, and content preparation for the analysis phase Project 14% complete overall Resource hours were less than planned
Key actions planned for the next phase (design) & Resources
Design Logo Design homepage with links Design the Navigation bar with JavaScript Design the Prototype Completion for Build Resources (Software + Applications, Fonts, Colors)
Total hours expected and Completion dates (design)
Design phase total planned hours are 455 Design phase 08/17/20 - 09/21/20
Cost trends against planned budget Budgeted hours used to date (hours/cost) | Budgeted hours needed for project completion (hours/ cost)
Analysis Phase | Design (455 hr/ $25,970.00)
Hours 264/275 | Build (700 hr/ $41,320.00)
Cost $ 14,866.00 / $15,595.00 | Test (260 hr/ $15,425.00)
 | Delivery (120 hr / $ 7,120.00)
Notes: Key accomplishments through end of the analysis phase was that we were able to complete all project tasks for this phase. We have completed14% of the project. We only utilized 264 of our 275 allotted resource hours. Completed all tasks for planning, layout and prototyping, content integration, and content preparation for the analysis phase.
Key actions planned for the next phase include the design logo, homepage layout, preparing and integrating our high-level requirements into the design structure, designing the navigation bar with JavaScript, and the creation of a prototype to start development. Our resources will include various software and applications, fonts, Color schematics, and User interface kits.
The total Planned hours to complete the design phase is 455 hours with an estimated phase completion date of 09/21/20.
Our forecasted project schedule is as follows, the analysis phase is complete. We just entered the design phase and we expect to complete this phase on 09/21/20. The project development phase is scheduled to be completed on 11/24/20. We estimate that the testing phase will be concluded on 12/22/20. We expect to deliver the finished product on 01/07/20.
Our cost trends show that we only utilized 264 of the allotted 275 hours and only $14,866.00 of the planned $15,595.00 for the analysis phase. This changes our estimated cost to complete the project from $105,430.00 to $100,502.00 which is $4,928.00 less then our original cost to complete. The project is currently on schedule and under budget. As you can see.
The total amount of planned hours left to complete the project is 1,535 hours. 455 hours to design, 700 hours to develop, 260 hours to complete testing and 120 hour to prepare the project to go live. The total remaining budget to complete for the rest of the project is $90, 564.00.

## Slide 4: Critical Path
Prior Period
This Period
Next Period
Executive Assistance Needed
Objective 1 Met
Objective 2 Met
Project Assumptions
None this period
Project Constraints
None this period
Project Staffing
No change
No executive assistance this period
Project success criteria
Effectively complete Analysis phase
Start design phase
This Photo by Unknown Author is licensed under CC BY-SA
Milestone
Analysis Phase
07/20/20- 08/14/20
Milestone
Design Phase 08/17/20 – 09/21/20
Milestone
Build Phase
09/21/20-11/24/20
Milestone
Test Phase
11/24/20 -12/22/20
Milestone
Delivery Phase
12/22/20 -01/07/20
Notes: Here’s our critical path objective 1 has been met and we have now started on objective 2.
The analysis phase was completed on 08/14/20 and our design phase is expected to be completed on 09/21/20.
We currently do not require executive assistance this period. We currently do no have any issues, risks, or changes to the scope. There are no project constraints at this time that will impact the schedule, budget, scope or quality of the project. Project assumptions have not changed since the initiation of the project.

## Slide 5
5
Mitigation & Action plan for risk & issues
XYZ Website Project
12/01/2020
Overall Status:
Action Plan
The project will closely monitored for potential risks, issues and scope changes.
Project milestones through current Period Design Phase | Target date | Expected completion | Status
Design | 08/17/20 | 09/01/20 | 
Design Review | 09/02/20 | 09/03/20 | 
Design Updates | 09/03/20 | 09/17/20 | 
Validate Design | 09/17/20 | 09/21/20 | 
Project Tracking
WBS Task completion monitoring No concerns Improvement
Key actions planned for the next [two weeks]
Create Design Artwork (08/17/20-08/18/20) Create Logo Design (08/18/20 – 08/20/20) Design Link to home-page (08/20/20-08/21/20) Add visuals to header with search option (08/21/20-08/24/20) Design Navigation in JavaScript, Verify content & Design (08/24/20-08/31/20)
Key Risks Issues Scope Changes
There have been no risks, issues or scope changes since the initiation of the project. There are no at risk situations or roadblocks There are no changes from the project constraints There have been no staffing changes since project kick-off There are no changes to project constraints listed in the project charter
Stakeholder Management Issues
There are no issues that the senior leadership team needs to address this period There is currently no action needed by Senior leadership to remain on task this period There are no changes from project assumptions
Project Metrics & Performance | Status
Budget | 
Schedule | 
Risk Management | 
Stakeholder Management | 
G
G
Legend: Major issues Some issues Satisfactory
R
O
G
G
G
G
G
G
G
G
This Photo by Unknown Author is licensed under CC BY-SA
Notes: We are currently using the sprint backlog and Work breakdown structure to track the project and manage any potential threats, risk or opportunities.
Team member tasks are being monitored and completed in Jira. We will continue to monitor the team effort. There are currently no project concerns. We will continue to look for ways to improve our process as we move forward.
Our Key actions planned for the next two weeks are as followed: the design artwork will be completed on 08/18/20. The company logo design will be completed on 08/20/20. On 08/21/20 the design for the home page link will be completed. Visuals with a search option will be completed on 08/24/20. The design for the page navigation using JavaScript will be completed on 08/31/20.
Here you can see that the project metrics and performance is satisfactory. There are currently no issues with the schedule, budget, risk or stakeholder management.
Our project Milestones through the design phase are that we started the initial design on 08/17/20 we will complete this phase on 09/01/20. The design review is expected to be completed on 09/03/20, Any updates or changed to the design will be completed on 09/17/20, and we expect to validate the design and hand it off to the development team on 09/21/20.
There are currently no roadblocks keeping us from moving forward. We have not had any staffing changes or changes to constraints since the project kickoff. At this time there are no stakeholder management issues however we will continue to monitor and keep stakeholders informed. The action plan at this time is to monitor the project for potential risk that may require an action plan.

## Slide 6: Thank You
Next Steps
Questions & Answers
I can be reached at shawnette.johnson31@gmail.com
Notes: The next steps is for the team to work on tasks schedule for the design phase. Are there any Questions? Thank you for your time. If you have any additional questions, please feel free to reach me by email at shawnette.johnson31@gmail.com