## Slide 1: XYZ Website Project Kickoff

## Slide 2: Welcome!
Hello I’m Shawnette Johnson
I am here to Kickoff the XYZ website Project Meeting
You can reach me by email: shawnette.johnson31@gmail.com

## Slide 3
Team Introductions
Notes: At this time I would like to open the floor up for introductions. I’m Shawnette Johnson and I’m the project manager assigned to this project. When I call your name would you please briefly introduce yourself.

## Slide 4: Meeting Ground Rules
We will start on time
Topics will only consist of agenda items
Please be respectful and courteous of others

## Slide 5: Agenda
Introduction of Project & Purpose
Project Team & Roles
Project Background
Project goals & objectives
Key Performance Indicators
Scope Review
Schedule Milestones
Risks & Issues
Project Reporting
Change Control
Collaboration Process &Tools
Deliverable Approval Process
Next Steps
Questions
1

## Slide 6: Project Kickoff Purpose
To design and develop a fully functional website for the XYZ company.
The website should have a professional look and provide an exceptional user experience.
We want to provide XYZ’s customers with the ability to shop online for products and services

## Slide 7: Project Background
The XYZ company is a new company that was established this year.
Senior Leadership of XYZ initially wanted a professional website but hired a small web hosting site to provide a generic layout.
The current site is simple, lacks graphic designs, and provides bare minimal XYZ company information.

## Slide 8
The Success Of Teamwork
Coming together is a beginning.
Keeping together is progress.
Working together is success.
~ Henry Ford~

## Slide 9: Project Team Roles
Name | Title & Role | Responsibilites
Tom Kane | XYZ Facilities Manager Project Sponsor | Evaluates the project progress Oversee high-level project progress Approves project deliverables, milestones, budget, and resources Approve project completion
Shawnette Johnson | ABC Web Designs Project Manager | Provides project planning and management Ensures that the project is completed to specification on time and under budget
Cindy Lewis | ABC Web Designs Consulting Analyst | Help improve performance by providing insight and solutions for organizational problems Conduct studies and surveys Analyze datasets and information
Helen Peters | ABC Web Designs Web Designer | Task to be determined by design lead

## Slide 10: Project Team Roles
Name | Title & Role | Responsibilities
Jason Morris | ABC Web Designs Senior Web Developer | Lead developers Identify user and system requirements Write code Review code work for accuracy Implement design plans Run functionality testing to debug code Liaise with designers to decide on UI/UX elements Delegate tasks to developers Complete network diagnostics Implement security Conduct mockups and UI prototyping
Scott Fassett | ABC Web Designs Senior Web Designer | Lead designers Determine website specifications Execute all visual design stages to final hand off Translate high-level requirements into flows and artifacts Create Wireframes, storyboards, user flows, and site maps Assign design tasks

## Slide 11: Team Structure
Tom Kane
Project Sponsor
Shawnette Johnson
Project Manager
Developers
Helen Peters
Designer
Cindy Lewis
Consultant Analyst
Scott Fassett
Senior Designer
Jason Morris
Senior Developer

## Slide 12: Project Goals and Objectives
To create a website that is fully operational within six months from the project launch date.
Increase the amount of returned customers
Increase sales by having a vast inventory of products and services
Create a backup of all company website information to be maintained offline in case of catastrophic failure.
Ensure that system errors or failures are kept below 3% per month based on total system transactions.
Ensure that the help desk is active between 7:00 AM and 8:00 PM seven days a week.

## Slide 13: Key Performance Indicators
Key performance for this project will be measured weekly using the following methods:
Project Budget Deviations
  How, where and why the project deviated from the budget
Deviation of Planned Hours Worked
  What tasks took more or less time then anticipated
Percentage of Milestones Missed
  What milestones where not achieved on time
Cost variance
  Completed work cost compared to the planned work cost

## Slide 14: Scope Review
Establish high-level project requirements.
Analyze requirements to design and build a new website.
Establish the estimated cost to design, build, test implement, and maintain the XYZ website for five years.
Finalize hosted website, provide ongoing support, and maintenance.
The website must be completed within 3-6 months from the project launch date.

## Slide 15: Milestone Schedule Review
11/02/2020
XYZ Project Launch
Project Launch
11/16/2020
Requirements
XYZ web requirements will be obtained and finalized
Requirements
11/30/2020
Design
XYZ project design draft will be complete
Design Draft
12/07/2020
Design Completion
The final web design will be presented
Design Presentation

## Slide 16: Milestone Schedule Review
01/26/2021
Web Development
Developers will complete web development.
Web Development
02/16/2021
Web-user Testing
Web-users will complete their testing.
Web-user Testing
03/16/2021
Live Beta Testing
Live Beta Testing will be complete.
Live Beta Testing Ends
04/06/2021
Beta Testing
The final updates from beta testing will be performed.
Beta Testing Updates
04/13/2021
Go Live
The Website will go Live.
Go Live

## Slide 17: Risks and Issues
After all requirements have been captured and understood, the project schedule may exceed the six-month target date for completion.
Changes in project staff may unexpectedly occur due to attrition requiring time to fill the position and transition the required work.
The wide area network and local area network have been recently unstable with relevant upgrades being made by the service providers. This may cause further delays in the project schedule once it has been baselined.

## Slide 18: Project Reporting
A weekly project status report will be provided detailing:
Cost performance
Schedule performance
Issues
Risks
The weekly status update will be distributed through the key stakeholder listing.
The stakeholder communication plan will provide a full list to be distributed to pertinent parties.
Stakeholders will receive all reports through email distribution.
The Project manager will be providing weekly status updates to the report with assistance from team leads.
The status reports will be provided to stakeholders once a week on Friday.

## Slide 19: Integrated Change Control
Initiation
Upon receiving notificaiton of a change request the project manager will record the change request into the project change log.
Process
The change request form will be completed.
The form should include a complete analysis of the change, cost, schedule impact and associated risks.
The request form is presented to the Change Control Board (CCB) for approval.
Approval
The project manager will respond to questions from the CCB.
If the change is approved the change log, project management plan, and any other project artifacts will be updated to support the change.
The project baseline will be updated to include changes to the schedule and cost.

## Slide 20: Collaboration Process & Tools
Zoom and Face to Face Meetings
Project collaboration, brainstorming, training, and team building exercises
Email
Preferred channel of communication
Backlog
          Create, assign, and update tasks
          Set project deadlines
          Collaborate on code
          View who’s working on what branch in the repository
          Monitor and track changes
          Create status reports

## Slide 21: Deliverable Approval Process
The project sponsor, will accept and approve each milestone before ABC Web Designs can proceed to the next milestone.
Deliverables will be accepted and approved following user testing.
Provide and approve budget and resources
Approve project completion.
The project Sponsor, will provide authorization for the work to be completed.
Deliverables are defined based on business needs and project scope.
The deliverables are defined in the project Requirements Document.

## Slide 22
Let’s get Started
Next Steps:
Start the work to complete the first milestone.

## Slide 23: THANKS!
The floor is open for questions?